## Module_Inventory
Module ID | Module Name | Business Requirement | Functional Requirement | Test Scenarios | Test Cases | Open Bugs | Closed Bugs | Priority | QA Status | Sprint
M-001 | Company Search | BR-002 | FR-003 | 12 | 10 | BUG-002 | BUG-001 | High | In Progress | Sprint 2
M-002 | Financial Statements | BR-003 | FR-005 | 2 | 1 | BUG-003 | - | High | In Progress | Sprint 2
M-003 | Company Overview | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-004 | Key Metrics | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-005 | Ratio Analysis | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-006 | Shareholding | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-007 | News | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-008 | Charts | TBD | TBD | 0 | 0 | - | - | Medium | Pending | Backlog
M-009 | Portfolio | TBD | TBD | 0 | 0 | - | - | High | Pending | Backlog
M-010 | Watchlist | TBD | TBD | 0 | 0 | - | - | High | Pending | Backlog
M-011 | Valuation | TBD | TBD | 0 | 0 | - | - | High | Pending | Backlog
M-012 | Forensics | TBD | TBD | 0 | 0 | - | - | High | Pending | Backlog
M-013 | Export | TBD | TBD | 0 | 0 | - | - | Low | Pending | Backlog
M-014 | Settings | TBD | TBD | 0 | 0 | - | - | Low | Pending | Backlog