## Test Scenarios
Scenario ID | Module | Requirement Ref | Scenario | Priority | Type | Status
TS-001 | Company Search | BR-002/FR-003 | Verify search box is displayed | High | UI | Not Executed
TS-002 | Company Search | BR-002/FR-003 | Verify live suggestions appear after entering 2 characters | High | Functional | Passed
TS-003 | Company Search | BR-002/FR-003 | Verify suggestions update while typing | High | Functional | Passed
TS-004 | Company Search | BR-002/FR-003 | Verify company can be selected from suggestions | High | Functional | Passed
TS-005 | Company Search | BR-002/FR-003 | Verify search using NSE ticker | High | Functional | Passed
TS-006 | Company Search | BR-002/FR-003 | Verify invalid search returns appropriate message | Medium | Negative | Not Executed
TS-007 | Company Search | BR-002/FR-003 | Verify Search Everywhere option navigates correctly | High | Regression | Failed (BUG-002)
TS-008 | Financial Statements | FR-005 | Verify Consolidated statement loads | High | Functional | Passed
TS-009 | Financial Statements | FR-005 | Verify Standalone statement loads | High | Regression | Failed (BUG-003)
TS-010 | Financial Statements | FR-005 | Verify Fetch 10-Year Data button loads data | High | Functional | Passed
TS-011 | Application | NFR | Verify application launches successfully | Critical | Smoke | Passed
TS-012 | Deployment | NFR | Verify production deployment is accessible | Critical | Smoke | Passed