## Test_Execution
Execution ID | Test Case ID | Scenario ID | Module | Executed By | Execution Date | Build/Version | Environment | Browser | Expected Result | Actual Result | Status | Bug ID | Remarks
EX-001 | TC-001 | TS-001 | Company Search | Rushikesh Shete | 2026-07-05 | v1.0.1 | Local (.venv) | Chrome | Search box displayed | Search box displayed | PASS |  | Smoke Test
EX-002 | TC-004 | TS-002 | Company Search | Rushikesh Shete | 2026-07-05 | v1.0.0 | Local (.venv) | Chrome | Live suggestions appear | Suggestions appeared only after Enter | FAIL | BUG-001 | Defect logged
EX-003 | TC-004 | TS-002 | Company Search | Rushikesh Shete | 2026-07-05 | v1.0.1 | Local (.venv) | Chrome | Live suggestions appear | Suggestions appear while typing | PASS | BUG-001 | Retest passed
EX-004 | TC-006 | TS-004 | Company Search | Rushikesh Shete | 2026-07-05 | v1.0.1 | Streamlit Cloud | Chrome | Company loads after selection | Company loaded successfully | PASS |  | Production smoke
EX-005 | TC-009 | TS-007 | Company Search | Rushikesh Shete | 2026-07-06 | v1.0.1 | Streamlit Cloud | Chrome | Correct page opens | Incorrect page/error | FAIL | BUG-002 | Open defect
EX-006 | TC-010 | TS-009 | Financial Statements | Rushikesh Shete | 2026-07-06 | v1.0.1 | Streamlit Cloud | Chrome | Standalone data loads | Standalone not loading | FAIL | BUG-003 | Open defect